## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
1 | Role assignment | 2018-01-26 | Team members are totally unknown to eachother. So it’s an issue to assign a proper role to everyone. | If we don’t know team members capablities then its hard to assign roles | Dhruv Patel | Dhruv Dabhi | Solved
2 | Meeting Place | 2018-01-26 | It is an issue to meet everytime on a specific place Because evryone has diffferent schedules and time managemnet. | If a team fails to meet at same place than its hard to do project work without coordination. | Meet Patel | Rushit Patel | Solved
3 | Scheduale Preparation | 2018-01-26 | Scheduale is a major issue.We have to make a proper schedule to do work. | If a team fails to make a schedule for work than its hard to meet project deadlines. | Raj Vaghela | Raj Vaghela | In Progress.
4 | Creation of project plan | 2018-01-26 | A project plan is main document of any project. So it is important to prepare it and update it on time. | If a team fails to create or maintain plan so its immposible to finish the project. | Dhruv Dabhi | Dhruv Dabhi | Solved
5 | Creation of Agenda | 2018-01-26 | Agenda of every meeting needs to be decided prior to meeting. | IF a team fails to decide meeting agenda then it really becomes difficult to discuss things in meeting. | Rushit Patel | Rushit Patel | Solved
6 | Creation of IAD Log | 2018-01-26 | IAD log is important document of any project. So it is important to prepare it and update it on time. | If a team fails to create IAD log than team will not be able to maintain the progress of the project. | Dip Patel | Dip patel | Solved
7 | Communication | 2018-02-02 | Communication Medium is required to provide Project information. | Its very difficult to arrange meeting on everyday basis and sharing of Project work is also necessary at the same time . | Jeane Fernandes | Dhruv Dabhi | Solved
8 | Environment Setup | 2018-02-02 | To perform the project we have to setup the environment as per the given instruction | If we are not able to setup the environment on our systems successfully than it will be affect our whole project. | Dhruv Dabhi | Dhruv Dabhi | Solved
9 | Creation of Test Strategy | 2018-02-05 | Test strategy document is important to define testing objective before starting testing process.So it is neccessory to prepare. | If we fail to create a appropriate test strategy than it will directly affect the overall project | Dhruv Patel | Dhruv Dabhi | Solved
10 | Reassign team members' roles | 2018-02-09 | To take maximum output from every member, it is good idea to assign that role in which everyone is good. | If anyone in the team has lack of interest in performing their role than it will affect on overall project. | Dhruv Patel | Dhruv Dabhi | Solved
11 | Updation of Test Strategy | 2018-02-16 | After giving presentation we found that some of the contents of the test strategy were not appropriate. | If the changes are not done as per the client's need than it will affect the overall project in the later stage. | Raj Vaghela | Dhruv Dabhi | Solved
12 | Creation of Use cases for website. | 2018-02-23 | To understand all functionality of website, it is very important to cover all the required use cases. | If we miss some use case scenarios than it will result in improper system testing. | Meet Patel | Dhruv Dabhi | Solved
13 | Missing Use cases | 2018-02-26 | In the given template some use cases were not present so we need to add missing use cases | If we miss some use case than it will result in improper system testing. | Rushit Patel | Meet Patel | Solved
14 | Rotation of roles and responsibilities in the team. | 2018-03-13 | It is important in the team to rotate roles and responsibilities so everyone in the team gets exposed to different areas. | It will help everyone to understand different roles and responsibilitis. | Rushit Patel | Dhruv Dabhi | Solved
15 | Work collaboratively on test scenarios | 2018-03-16 | We need to work in collaboration with other team members | Team will be able to develop test scenarios very efficiently | Dhruv Dabhi | Dhruv Dabhi | Solved
16 | Select Test Scenarios template | 2018-03-16 | We need to select a template for test scenarios | We need a template to develop the test scripts so that every member has the same format | Dhruv Dabhi | Dhruv Dabhi | Solved
17 | Select the presentation date for test scenarios | 2018-03-16 | We have options to choose Tuesday and Friday for presenting test scenarios |  | Rushit Patel | Rushit Patel | Solved
18 | Issue of missing tests cases | 2018-03-16 | Several Test Cases were missing in the last document | The test cases should be added in the next document | Dhruv Dabhi | Dhruv Dabhi | Solved
19 | Determining Manual or Automated | 2018-03-16 | It is important to deteremine which test cases will be executed Manually and with Automated Driver | The test case will be executed as descibed | Dhruv Dabhi | Dhruv Dabhi | Solved
20 | Defining severity of test cases | 2018-03-18 | It is important to define which testcases are more important for our project so we can focus more on their execution. | Test cases with high severity will need more attention. | Dhruv patel | Meet Patel | solved
21 | Started execution of tests | 2018-03-18 | we are at the execution phase of tests | Execution will show if our testcases are failed or pass | Dip Patel | Dhruv dabhi | Solved
22 | Deciding dates for next meeting | 2018-03-19 | for our execution phase we have to decide meeting for date to start execution | Execution is the main phase of project | Rushit Patel | Meet Patel | solved
23 | Role assigned for execution | 2018-03-19 | For execution it is important to assign role to each team member | Team memebr can work on their role | Raj Vaghela | Meet Patel | solved
24 | Status report discussion | 2018-04-12 | What data we should include in status report | It is a important thing in our project | Dip Patel | Meet Patel | Solved
25 | Discussion on updating report | 2018-04-20 | After giving presentation we found that some of the contents of the bug report were not appropriate. | If the changes are not done as per the client's need than it will affect the overall project in the final stage. | Dhruv Dabhi | Dhruv Patel | Solved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
1 | 1 | Everyone gave introduction about their capabilities so roles were assigned as per their area of expertise. | 2018-01-26 | Roles were Assigned Properly | Dhruv Dabhi | Completed
2 | 2 | Meeting Place decieded as per everyones convineance. | 2018-01-26 | Everyone agreed upon meeting place. | Meet Patel | Completed
3 | 3 | Everyone gave their availabilities. | 2018-01-26 | Schedule is updated | Raj Vaghela | Completed
4 | 4 | Everyone shared their experience about creation of project plan and gave suggestion. | 2018-01-26 | Project plan is created | Dhruv Dabhi | Completed
5 | 5 | Everyone gave suggestions for meeting agenda. | 2018-01-26 | Meeting agenda created. | Rushit patel | Completed
6 | 6 | Everyone agreed to assign a person to create an IAD log. | 2018-01-26 | IAD log created | Dip Patel | Completed
7 | 7 | Created WhatsApp group for casual conversation relevant to Project work.And Gmail Group is created to share the Project files. | 2018-02-02 | Communication medium is created | Dhruv Dabhi | Completed
8 | 8 | The environment setup has been completed successfully one every team members systems. | 2018-02-02 | Environment Setup completed | Dhruv Dabhi | Completed
9 | 9 | All team members done brain storming and discussed ideas for test strategy and divided work as per team members preffered choices. | 2018-02-05 | Work devided to create test strategy document | Dhruv Dabhi | Completed
10 | 10 | Reassigned the roles to each group member • Project Manager : Dhruv Dabhi • Scribe : Rushit Patel • Automation Tester : Meet Patel • Manual Tester : Dhruv Patel • Test Manager : Dip Patel • Developer: Raj Vaghela • MySQL Developer : Jeane Fernandes | 2018-02-09 | Roles were Reassigned | Dhruv Dabhi | Completed
11 | 11 | Changes has been made in test strateghy template as per client's requirement. | 2018-02-19 | Test strategy updated. | Dhruv Dabhi | Completed
12 | 12 | Brain storming has been done by team and use cases are created. | 2018-02-26 | Created Use cases. | Dhruv Dabhi | Completed
13 | 13 | Basic Test Case templated has been created | 2018-02-27 | Tracebility matrix has been created | Meet Patel | Completed
14 | 14 | Created an online spreadsheet on which every member can work simultaneously | 2018-03-13 | Google Spreadsheet created | Dhruv Dabhi | Completed
15 | 15 | Test scenarios template was selected an distributed within the team | 2018-03-13 | Every member has the template | Dhruv Dabhi | Completed
16 | 19 | The Role of the Project Manager was assigned to Rushit Patel and Raj Vaghela was assigned the role of Scribe. | 2018-03-13 | Rushit Patel will be the Project Manager an Raj Vaghela will be the Scribe for next week. | Dhruv Dabhi | Completed
17 | 16 | Selected Tuesday, March 20 for Test Scenarios presentation | 2018-03-16 | We have 4 days to work on test scenarios | Rushit patel | Completed
18 | 17 | Missing test cases were noted and planned to be added in the next document | 2018-03-16 | Test cases should be added till the next meeting | Dhruv Dabhi | Completed
19 | 18 | Test cases document updated with 'M' for Manual testing and 'A' for automated testing | 2018-03-16 | Easy to determine which case should be executed manually or with automated tool | Dhruv Dabhi | Completed
20 | 20 | Stared defining severity accoring to requirments | 2018-03-18 | It will make easy to do important test cases first | Meet Patel | Completed
21 | 21 | Started execution of tests | 2018-03-18 | Execution will show the defects from the system. | Rushit patel | Completed
22 | 22 | All team members seggested meeting date | 2018-03-19 | We will able to do execution | Meet Patel | Completed
23 | 23 | Everyone deissced on their capablities | 2018-03-19 | Team can perform well | Meet Patel | Completed
24 | 24 | Everyone gave opinion about their views | 2018-04-12 | So status report can have enough data to represent test results | Meet Patel | Completed
25 | 25 | Changes has been made in defact report as per client's requirement. | 2018-04-21 | Defect report has been updated | Dhruv Patel | Completed

## Decisions
ITEM# | COMPLETION DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
1 | 2018-01-26 | Decision taken to assign roles | Roles are assigned. | 1
2 | 2018-01-26 | Decision taken to decide Meeting Place | Meeting Place is decided. | 2
3 | 2018-01-26 | Decision taken about Schedule | Scheedule is created. | 3
4 | 2018-01-26 | Decision taken to Project Plan | Project Plan is created. | 4
5 | 2018-01-26 | Decision taken to prepare Meeting Agenda | Meeting Agenda is decided. | 5
6 | 2018-01-26 | Decision taken to create IAD log | IAD log is created. | 6
7 | 2018-02-02 | Decision taken to create Communication medium | Communication medium is created | 7
8 | 2018-02-02 | Decision has been made on setting up the environment | Environment setup complete | 8
9 | 2018-02-05 | Decision taken about which area of Test Strategy every member will work on | Test Strategy document created | 9
10 | 2018-02-09 | Decision taken to assign roles as per member's interest. | Roles are reassigned. | 10
11 | 2018-02-19 | Decision has been made to update test strategy template. | Test Strategy document updated | 11
12 | 2018-02-26 | Decision has been taken to create use cases for the system. | Use cases template is created | 12
13 | 2018-02-26 | Decision has been taken to create Test cases for the system. | Tracebility-Matrix has been created | 13
14 | 2018-02-27 | Decision has been taken to create an online spreadsheet where all member can work simultaneously. | Google DOC created | 13
15 | 2018-03-13 | Decision taken to reassign the roles so that every member in the team gets chance to understand different roles and responsibilities | Roles were reassigned | 19
16 | 2018-03-16 | Decision has been taken to create Google Spreadsheet. | Google Spreadsheet created | 14
17 | 2018-03-16 | Decision has been taken to use the template given by the project sponser | Test Scenarios template downloaded | 15
18 | 2018-03-16 | Decision has been taken to select March 20 for presentation at 5:45 PM | Team members are notified about the specifics and the team has 4 days to work on the test scenarios | 16
19 | 2018-03-16 | Decision taken on creating missing test cases | Each members was given the responsibilities to develop missing test cases | 17
20 | 2018-03-16 | Decision taken to put 'M' or 'A' in the notes in the test case | Test case can be easily identified with the test type | 18
21 | 2018-03-18 | Decision taken to mark testcases by 'High','Medium','low' | test cases will be easy to find by severity | 20
22 | 2018-03-18 | Decision taken to start the execution using testing tools defined early. | test execution started | 21
23 | 2018-03-19 | Decision taken to meet on 22 march, 28 march and 4 april | meeting place decided | 22
24 | 2018-03-19 | Roles are assigned to everyone | Each team meber gets work on their area of experties | 23
25 | 2018-04-12 | Data is decide to enter in status report | Stauts report format is ready | 24
26 | 2018-04-21 | Decision has been made to update status report. | Status report updated | 25

## Team
INFO6068 | Capstone Project
Team Name: | Bug Benders
Members: | Dhruv Dabhi
Rushit Patel
Meet Patel
Dip Patel
Dhruv Patel
Raj Vaghela
Jeane Fernandes