## Summary
Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
Total number of test cases | 85
Number of testers | 7
Test cycle duration | 4 days
Overall status | Count |  |  | Defect severity | Number
TCs planned | 85 |  |  | Critical | 3
TCs executed | 85 |  |  | High | 12
Open Defects | 61 |  |  | Medium | 7
Number of test cases Blocked/No run | 41 |  |  | low | 7
Defects count | 29
Module-wise status
Execution Date | Module | Total | Pass | Fail | Blocked
2018-03-22 | User | 9 | 0 | 2 | 7
2018-03-22 | Reservation | 10 | 0 | 0 | 10
2018-04-04 | Routes | 9 | 8 | 0 | 1
2018-04-04 | Database | 6 | 2 | 0 | 4
2018-03-28 | Admin | 35 | 8 | 5 | 22
2018-04-11 | Automation (testimonial + admin + routes) | 16 | 7 | 8 | 1
2018-04-11 | Total | 85 | 25 | 15 | 45
Overall status
Number of test cases planned | 85
Number of test cases executed | 85
Pass Percentage | 32%
Defects density | 5.25 per day
Critical defects percentage | 8.4%
Status for 22/03/2018 |  |  | Status for 28/03/2018 |  |  | Status for 04/04/2018 |  | Status for 11/04/2018
Number of test cases planned | 19 |  | Number of test cases planned | 35 |  | Number of test cases planned | 15 | Number of test cases planned | 16
Number of test cases executed | 19 |  | Number of test cases executed | 35 |  | Number of test cases executed | 15 | Number of test cases executed | 16
Number of test cases executed overall | 19 |  | Number of test cases executed overall | 54 |  | Number of test cases executed overall | 69 | Number of test cases executed overall | 85
Number of defects encountered today | 5 |  | Number of defects encountered today | 14 |  | Number of defects encountered today | 5 | Number of defects encountered today | 7
Number of defect encountered so far | 5 |  | Number of defect encountered so far | 17 |  | Number of defect encountered so far | 22 | Number of defect encountered so far | 29
Number of defects- still open | 5 |  | Number of defects- still open | 17 |  | Number of defects- still open | 22 | Number of critical defects- still open | 29

## Detailed Status
Module | Test Case id | Test case Description | Responsible tester | Date of execution | Status (pass/fail/blocked) | Automated / Manual | DefectID | severity | status
user | TCTMLN001 | Test User Log in Page | Dhruv Dabhi | 2018-03-22 | Fail | M | TM001 | 1 - Critical | Open
user | TCTMLN002 | User login ID standard | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLN003 | User Password standard | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLN004 | Show password | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLN005 | Invalid user log in | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLN006 | User log in failure redirect | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLT001 | User logout | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
user | TCTMLT002 | User logout redirect | Dhruv Dabhi | 2018-03-22 | Blocked | M | TM001 | 1 - Critical | Open
routes | TCRMVR001 | User view the routes | Dhruv Dabhi | 2018-04-11 | Pass | A | TM001 | 1 - Critical | Open
routes | TCRMVR002 | User view the routes by date | Dhruv Dabhi | 2018-04-11 | Fail | A | TM008 | 3 - Medium | Open
routes | TCRMVR003 | Test the number of routes per page | Dhruv Dabhi | 2018-04-11 | Blocked | A | TM001 | 1 - Critical | Open
routes | TCRMVR004 | Test details of arrival and departure time of routes | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMVR005 | test details of start and end city of routes | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMVR006 | Test details of bus id of routes. | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMVR007 | Test details of fare of the routes. | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMPP001 | Test view pick up points redirect | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMPP002 | Test number of pick up points displayed | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMPP003 | Test View Pickup Points windows font size | Rushit Patel | 2018-04-04 | Pass | M
routes | TCRMPP004 | Test View Pickup Points window background color | Rushit Patel | 2018-04-04 | Pass | M
travel | TCRMVT001 | User Views the Travel agency | Rushit Patel | 2018-04-04 | Blocked | M | TM002 | 1 - Critical | Open
reservation | TCRMBT001 | The valid input to book tickets | Meet Patel | 2018-03-22 | Blocked | M | TM003 | 2 - High | Open
reservation | TCRMBT002 | The invalid input of date to book tickets | Meet Patel | 2018-03-22 | Blocked | M | TM003 | 2 - High | Open
reservation | TCRMBT003 | The invalid input of city to book tickets | Meet Patel | 2018-03-22 | Blocked | M | TM003 | 2 - High | Open
reservation | TCRMBT004 | The invalid input of a number of passengers to book tickets | Meet Patel | 2018-03-22 | Blocked | M | TM003 | 2 - High | Open
reservation | TCRMBT005 | The invalid input of a number of passengers to book tickets | Meet Patel | 2018-03-22 | Blocked | M | TM003 | 2 - High | Open
reservation | TCRMCT001 | The valid input to cancel tickets | Meet Patel | 2018-03-22 | Blocked | M | TM004 | 2 - High | Open
reservation | TCRMCT002 | The invalid input to cancel tickets | Meet Patel | 2018-03-22 | Blocked | M | TM004 | 2 - High | Open
reservation | TCRMCT003 | cancel the booked ticket in allowed time | Meet Patel | 2018-03-22 | Blocked | M | TM004 | 2 - High | Open
reservation | TCRMCT004 | cancel the booked ticket is not - allowed time | Meet Patel | 2018-03-22 | Blocked | M | TM004 | 2 - High | Open
reservation | TCRMCT005 | cancel the booked tickets with invalid email id | Meet Patel | 2018-03-22 | Blocked | M | TM004 | 2 - High | Open
testimonials | TCTMGT001 | The valid input to testimonials | Meet Patel | 2018-04-11 | Pass | A
testimonials | TCTMGT002 | the invalid input of email id to testimonials | Meet Patel | 2018-04-11 | Fail | A | TM005 | 3 - Medium | open
testimonials | TCTMGT003 | the invalid input of feedback to testimonials | Meet Patel | 2018-04-11 | Pass | A
testimonials | TCTMGT004 | the invalid input of feedback to testimonials | Meet Patel | 2018-04-11 | Fail | A | TM006 | 4 - low | open
testimonials | TCTMVT001 | view testimonials | Meet Patel | 2018-04-11 | Pass | A
Admin | TCAMUL001 | Admin Valid Login | Dhruv Patel | 2018-04-11 | Pass | A
Admin | TCAMUL002 | Admin Invalid Login | Dhruv Patel | 2018-04-11 | Fail | A | AM001 | 1 - Critical | Open
Admin | TCAMUL003 | Admin Login page font size | Dhruv Patel | 2018-03-28 | Pass | M
Admin | TCAMAU001 | Add User | Dhruv Patel | 2018-03-28 | Blocked | M | AM009 | 2 - High | Open
Admin | TCAMAU002 | Add Duplicate User | Dhruv Patel | 2018-03-28 | Blocked | M | AM009 | 2 - High | Open
Admin | TCAMAU003 | Add User page background color | Dhruv Patel | 2018-03-28 | Blocked | M | AM009 | 2 - High | Open
Admin | TCAMAU004 | Add User page font size | Dhruv Patel | 2018-03-28 | Blocked | M | AM009 | 2 - High | Open
Admin | TCAMAU005 | Add more than one users at the time | Dhruv Patel | 2018-03-28 | Blocked | M | AM009 | 2 - High | Open
Admin | TCAMVU001 | View User | Raj Vaghela | 2018-03-28 | Blocked | M | AM010 | 2 - High | Open
Admin | TCAMVU002 | View User page background color | Raj Vaghela | 2018-03-28 | Blocked | M | AM010 | 2 - High | Open
Admin | TCAMVU003 | View User page font size | Raj Vaghela | 2018-03-28 | Blocked | M | AM010 | 2 - High | Open
Admin | TCAMDU001 | Delete Valid User | Raj Vaghela | 2018-03-28 | Blocked | M | AM011 | 2 - High | Open
Admin | TCAMDU002 | Delete Invalid User | Raj Vaghela | 2018-03-28 | Blocked | M | AM011 | 2 - High | Open
Admin | TCAMDU004 | Delete User page font size | Raj Vaghela | 2018-03-28 | Blocked | M | AM011 | 2 - High | Open
Admin | TCAMCP001 | Change Password | Raj Vaghela | 2018-03-28 | Blocked | M | AM012 | 2 - High | Open
Admin | TCAMCP002 | Change Password Invalid | Raj Vaghela | 2018-03-28 | Blocked | M | AM012 | 2 - High | Open
Admin | TCAMCP003 | Change Password response | Raj Vaghela | 2018-03-28 | Blocked | M | AM012 | 2 - High | Open
Admin | TCAMAR001 | Add Route | Dhruv Patel | 2018-04-11 | Fail | A | AM002 | 2 - High | Open
Admin | TCAMAR002 | Add Multiple Route | Raj Vaghela | 2018-03-28 | Pass | M
Admin | TCAMAR003 | Add Invalid Route | Dhruv Patel | 2018-04-11 | Fail | A | AM003 | 2 - High | Open
Admin | TCAMAR004 | View Route update time | Raj Vaghela | 2018-03-28 | Blocked | M | AM016 | 2 - High | Open
Admin | TCAMVR001 | View Routes | Raj Vaghela | 2018-03-28 | Pass | M
Admin | TCAMVR002 | View Routes Details | Dhruv Patel | 2018-03-28 | Pass | M
Admin | TCAMVR003 | View Route Order by date & Time | Dip Patel | 2018-03-28 | Fail | M | AM004 | 4 - low | Open
Admin | TCAMVR004 | View Route Updates | Raj Vaghela | 2018-03-28 | Blocked | M | AM016 | 2 - High | Open
Admin | TCAMVR005 | View Route Availability | Jeane Fernandes | 2018-03-28 | Pass | M
Admin | TCAMDR001 | Delete Route | Dhruv Patel | 2018-04-11 | Fail | A | AM005 | 3 - Medium | Open
Admin | TCAMDR002 | Test delete route page background color | Jeane Fernandes | 2018-03-28 | Fail | M | AM015 | 4 - low | Open
Admin | TCAMDR003 | Test delete route page Font Size | Dip Patel | 2018-03-28 | Pass | M
Admin | TCAMDR004 | Test delete route redirect page | Dip Patel | 2018-03-28 | Fail | M | AM006 | 4 - low | Open
Admin | TCAMDR005 | Admin deletes more than one routes at the time | Dip Patel | 2018-03-28 | Pass | M
Admin | TCAMDR006 | Delete Route Details | Dip Patel | 2018-03-28 | Fail | M | AM017 | 4 - low | Open
Admin | TCAMRP001 | Admin Remove place | Jeane Fernandes | 2018-03-28 | Blocked | M | AM013 | 2 - High | Open
Admin | TCAMVP001 | Admin Views place | Jeane Fernandes | 2018-03-28 | Blocked | M | AM013 | 2 - High | Open
Admin | TCAMVB001 | Admin Views booking | Jeane Fernandes | 2018-03-28 | Blocked | M | AM013 | 2 - High | Open
Admin | TCAMLT001 | Admin logout | Dhruv Patel | 2018-04-11 | Pass | A
Admin | TCAMLT002 | Automatic logout | Dip Patel | 2018-03-28 | Fail | M | AM007 | 4 - low | Open
Admin | TCAMCB001 | Confirm Booking | Jeane Fernandes | 2018-03-28 | Blocked | M | AM014 | 2 - High | Open
Admin | TCAMRB001 | Reject Booking | Jeane Fernandes | 2018-03-28 | Blocked | M | AM014 | 2 - High | Open
Admin | TCAMAT001 | Admin adds travel agency | Dhruv Patel | 2018-04-11 | Pass | A
Admin | TCAMVT001 | Admin views Travel Agencies | Dip Patel | 2018-03-28 | Pass | M
Admin | TCAMDT001 | Admin deletes travel agency | Dhruv Patel | 2018-04-11 | Fail | A | AM008 | 3 - Medium | Open
Admin | TCAMAP001 | Admin Adds places | Jeane Fernandes | 2018-03-28 | Blocked | M | AM013 | 2 - High | Open
Database | TCUMDU001 | Database update for valid ticket booking | Dip Patel | 2018-04-04 | Fail | M | DM001 | 2 - High | Open
Database | TCUMDU002 | Database update for valid ticket cancellation | Dip Patel | 2018-04-04 | Fail | M | DM002 | 2 - High | Open
Database | TCUMDU003 | Update in feedback database. | Dip Patel | 2018-04-04 | Pass | M
Database | TCUMDU005 | Update in route-master database. | Dip Patel | 2018-04-04 | Fail | M | DM003 | 3 - Medium | Open
Database | TCUMDU006 | Update ticket availability in route-master database. | Dip Patel | 2018-04-04 | Fail | M | DM004 | 3 - Medium | Open
Database | TCUMDU007 | Update in travelsmaster database | Dip Patel | 2018-04-04 | Pass | M
user | TCUM01 | user tries to run application on fireforx and microsoft edge. | Meet Patel | 2018-03-22 | Fail | M | TM007 | 3- Medium | Open

## Bug Report
DefectId | Test script ID | Defect Description | Step to reproduce | Severity | State | Version | created by | Assign to
TM001 | TCTMLN001 | No user login page | 1. User must be on the home page2. User clicks on Login page Expected Result: There should be user login page Actual Result: There is no login page | 1 - Critical | Open | 1 & 2 | Dhruv Dabhi | Dhruv Dabhi
TM002 | TCRMVT001 | No Travel module in application | User must be logged in | 1 - Critical | open | 1 & 2 | Rushit Patel | Rushit Patel
user clicks on book tickets tab
user can see travel agenses to book tickets
TM003 | TCRMBT001 | Date field is not working | User must be logged in User is on Book tickets page Select Departure City Select Destination City Journy date Bus type Number of passenger user clicks on book ticket tab | 2 - High | open | 1 & 2 | Meet Patel | Meet Patel
TM004 | TCRMCT001 TCRMCT002 TCRMCT003 TCRMCT004 TCRMCT005 | Cancel ticket button is not working | Tickets are booked User must be logged in User is on cancel tickets page user enters email address user enters booking ID user clicks on cancel booking | 2 - High | open | 1 &2 | Meet Patel | Meet Patel
TM005 | TCTMGT002 | Email field is accepting all kind of text. | User is logged in user is on Testimonials user enters email address user writes feedback user clicks on submit button | 3 - Medium | open | 1 & 2 | Meet Patel | Meet Patel
TM006 | TCTMGT004 | Feedback field is accepting more than 200 charactors | User is logged in user is on Testimonials user enters email address user writes feedback user clicks on submit button | 4 - Low | open | 1 & 2 | Meet Patel | Meet Patel
TM007 | TCUM01 | Application also runs on different browser | Database and tomcat is in active state. user runs applicaion on firefox and edge | 3 - Medium | open | 1 & 2 | Meet Patel | Meet Patel
TM008 | TCRMVR002 | Fields can not be sorted with date | User is logged in User navigates to view routes Tries to sort the routes by date | 3 - Medium | Open | 1 & 2 | Dhruv Dabhi | Dhruv Dabhi
AM001 | TCAMUL002 | Admin able to get login with wrong user_id and password. | Admin click on "Admin Login" button. | 1 - Critical | Open | 2 | Dhruv | Dhruv
Admin insert wrong Id and password.
Admin click on Submit button.
Expected result: System show login failed error.
Actual result: Admin able to log into system.
AM002 | TCAMAR001 | Unable to add route data because mandatory fields can not be selected | Admin click on "Add Route" button. | 2 - High | Open | 2 | Dhruv | Dhruv
Admin insert route datails.
Admin click on add button.
Expected result: Route's details successfully added to the system.
Actual result: Can't able to select mandatory fields which shows errors.
AM003 | TCAMAR003 | Unable to add route data with invalid data because mandatory fields can not be selected | Admin click on "Add Route" button. | 2 - High | Open | 2 | Dhruv | Dhruv
Admin insert invalid route datails.
Admin click on add button.
Expected result: System shows error message.
Actual result: Can't able to select mandatory fields which shows errors.
AM004 | TCAMVR003 | There is no any options for arranging date and time | Admin must be logged-in | 4 - Low | Open | 2 | Dip | Dip
Admin clicks on view route button
Admin view routes in the system
Admin tries to find arranging date and time
Expected result: The displayed route should be arranged in proper order by their date and departure time
Actual result: Date and time did not arranged in a proper order
AM005 | TCAMDR001 | Can't able to delete route. Shows null pointer error. | Admin click on "Delete Route" button. | 3 - Medium | Open | 2 | Dhruv Patel | Dhruv Patel
Admin selects route Id.
Admin click on delete button.
Expected result: Route detail should be deleted from the system.
Actual result: Can't able to delete route. Shows null pointer error.
AM006 | TCAMDR004 | While deleting route when we click on delete buttton we didn't able to redirect page of view delete. | Admin must be logged-in | 4 - Low | Open | 2 | Dip | Dip
Admin clicks on delete route button
Admin select route ID
Admin clicks on delete button
Expected result: After deleting a route, admin should be redirected to delete route page.
Actual result: Admin didn't able to redirect to delete route page
AM007 | TCAMLT002 | Website didn't respond when system is inactive for 10mins | Admin must be logged-in | 4 - Low | Open | 2 | Dip | Dip
Put system in inactive mode
Expected result: Admin should successfully logged-out after 10 mins of inactivity
Actual result: There should not be automatic logged-out functionality work after inactivity of 10mins
AM008 | TCAMDT001 | Can't able to delete travel agency. | Admin click on "Delete Travel" button. | 3 - Medium | Open | 2 | Dhruv Patel | Dhruv Patel
Admin selects travel Id.
Admin click on delete button.
Expected result: Travel detail should be deleted from the system.
Actual result: Can't able to delete travel. Shows null pointer exception error.
AM009 | TCAMAU001, TCAMAU002, TCAMAU003, TCAMAU004, TCAMAU005 | System doesn't have "Add User" page | Admin must be logged-in | 2 - High | open | 2 | Dhruv Patel | Dhruv Patel
Admin click on "Add User" button.
Expected result: Add user page should be open.
Actual result: Doesn't have Add User page.
AM010 | TCAMVU001, TCAMVU002, TCAMVU003 | System doesn't have "View User" page | Admin must be logged-in | 2 - High | open | 2 | Raj Vaghela | Raj Vaghela
Admin click on "View User" button.
Expected result: View user page should be open.
Actual result: Doesn't have View User page.
AM011 | TCAMDU001, TCAMDU002, TCAMDU004 | System doesn't have "Delete User" page | Admin must be logged-in | 2 - High | open | 2 | Raj Vaghela | Raj Vaghela
Admin click on "Delete User" button.
Expected result: Delete user page should be open.
Actual result: Doesn't have Delete User page.
AM012 | TCAMCP001, TCAMCP002, TCAMCP003 | System doesn't have change password option. | Admin must be logged-in | 2 - High | open | 2 | Raj Vaghela | Raj Vaghela
Admin click on "change password" button.
Expected result: Admin able to change password.
Actual result: System doesn't have change password option.
AM013 | TCAMRP001, TCAMVP001, TCAMVB001, TCAMAP001 | System doesn't have "Add Place" page | Admin must be logged-in | 2 - High | open | 2 | Jeane Fernandes | Jeane Fernandes
Admin click on "Add Place" button.
Expected result: Add Place page should be open.
Actual result: Doesn't have Add Place page.
AM014 | TCAMCB001, TCAMRB001 | System doesn't have booking option in admin module. | Admin must be logged-in | 2 - High | open | 2 | Jeane Fernandes | Jeane Fernandes
Admin click on "View Booking" button.
Expected result: Admin able to view booking and confirm or reject them.
Actual result: System doesn't have booking option in admin module.
AM015 | TCAMDR002 | Delete route page background color does not white. | Admin must be logged-in | 4 - Low | Open | 2 | Jeane Fernandes | Jeane Fernandes
Admin click on "Delete route" button.
Expected result: Delete route page background color should be white.
Actual result: Delete route page background color is light blue.
AM016 | TCAMAR004, TCAMVR004 | Not option for update route on view route page | Admin must be logged-in | 4 - Low | open | 2 | Raj Vaghela | Raj Vaghela
Admin click on "View route" button.
Expected result: Update route option available on View route page.
Actual result: Update route option not available on View route page.
AM017 | TCAMDR006 | Doesn't show selected route Id details on delete route page. Show detail button not working | Admin must be logged-in | 4 - Low | Open | 2 | Dip Patel | Dip Patel
Admin click on "Delete route" button.
Admin select route Id.
Admin click on view details button.
Expected result: Show selected route Id details.
Actual result: Doesn't show selected route Id details on delete route page. Show detail button not working.
DM001 | TCUMDU001 | Date field and check availability field in book ticket is not working so we can't book ticket | The user is logged in User try to book ticket | 2 - High | Open | 1 & 2 | Dip | Dip
User is on Book Tickets Page
User try to book ticket
Expected result: Tickets are confirmed with booking id. Booking id and user's email id are stored in database.
Actual result: User can't able to book ticket successfully anf database is not updated
DM002 | TCUMDU002 | We can't check ticket database connectivity with the cancel ticket function because cancel ticket button doesn't work. | The user is logged in | 2 - High | Open | 1 & 2 | Dip | Dip
Ticket is already booked
User is on Cancel Tickets Page
User try to cancel ticket.
Expected result: Booking is canceled. Booking id and user's email id are deleted from database.
Actual result: User didn't able to book ticket sucessfully and database is not updated
DM003 | TCUMDU005 | We can't perform this test as add route functionality is not working. | Admin must be logged-in. | 3 - Medium | Open | 1 & 2 | Dip | Dip
Admin wants to add new route and route must not be already added in the system
Expected result: Route details are added in the route-master database.
Actual result: Route details are not added in the route-master database and database is not updated
DM004 | TCUMDU006 | In ticket booking module check availability button is not working so we can't check ticket availability | The user is logged in | 3 - Medium | Open | 1 & 2 | Dip | Dip
User is on Book Tickets Page and try to book ticket.
Expected result: Ticket is booked and ticket availability is updated in to the system
Actual result: Database is not updated as in ticket booking module date and check availability fields are not working,